## 01_Title
reBot-DevArm B601-DM
V-MODEL TEST PLAN — Unit · Integration · System
Document ID | REBOT-TST-CP-001
Revision | 0.1 (draft)
Issue date | 2026-05-04
Author | J. Herrod-Thomas
Item | reBot-DevArm B601-DM
Standards basis | IEEE 829-2008; ISO 13849-2; ISO 10218 + TS 15066
Linked artefacts | REBOT-SC-CP-001 · REBOT-REQ-CP-001 · REBOT-DFMEA-CP-001 · REBOT-ARCH-CP-001
Coverage target | 100 % of safety reqs verified by ≥1 test; ≥80 % FW statement coverage

## 09_Stats
Test Plan KPI Dashboard
Total tests | Unit | Integration | System | Safety-rated | Auto/T method
127 | 82 | 23 | 22 | 83 | 104
Tests by V-model level
Level | Count
Unit | 82
Integration | 23
System | 22

## 02_Strategy
Test Strategy & V-Model
Scope | Verification of all 104 requirements (SyRS+SRS+HwRS) plus validation of the 31 safety functions per ISO 13849-2 and ISO 10218 + ISO/TS 15066. Concept-phase test definition.
V-Model layers | Unit (left arm of V): per-component tests on FW, HW, mechanical, document. Integration: subsystem-boundary tests across host↔motor bus, E-Stop chain, ROS2 driver. System (right arm): operating-envelope behaviour, ISO 13849-2 Table B.1 procedures, TS 15066 PFL measurement.
Verification methods | I = Inspection; A = Analysis (FEA, simulation); T = Test (formal); D = Demonstration (observed).
Acceptance criteria | (a) Every safety req verified by ≥ 1 system test. (b) Every High-AP DFMEA failure mode has a test exercising the mitigation. (c) Statement coverage on safety-tagged FW ≥ 80 %. (d) ISO 13849-2 procedures pass for SF-01..SF-31 at allocated PL. (e) TS 15066 PFL measurement campaign complete.
Entry criteria | Architecture frozen at the level under test. Item built and identified. Test environment calibrated. Test cases peer-reviewed.
Exit criteria | All planned tests executed; defects triaged; safety-relevant defects fixed and retested OR documented as residual risk in the safety case with assessor sign-off.
Independence | ISO 13849-2 §5 requires validation by personnel independent of designers. The Owner column flags 'Test' for the independent test team; FW/EE/Mech tasks may be self-verified at unit level but require independent verification at integration / system level for safety-rated items.

## 06_ISO13849v
ISO 13849-2 Validation Matrix (per safety function)
SF | Description | PLr | Validation activity per ISO 13849-2 Table B.1 | Linked TC
SF-01 | PFL per ISO/TS 15066 | d | TS 15066 force/pressure measurement + jerk-limit + sensor-fusion fault | TC-S-002, TC-S-045, TC-S-046, TC-U-037
SF-02 | Soft-stop on contact-force threshold | d | Function check + fault injection | TC-S-046, TC-U-028
SF-03 | Joint torque/velocity limit | d | Function + boundary + cross-monitor | TC-U-001, TC-U-002, TC-S-003, TC-U-022
SF-04 | Force-limited contact | d | TS 15066 PFL measurement + collision injection | TC-S-002
SF-05 | Sharp-edge mitigation | — | Inspection | TC-U-050
SF-06 | Speed reduction in shared workspace | c | Function + perception fault | TC-I-025, TC-S-022
SF-07 | Pinch-zone gap ≤ 4 mm | — | ISO 13854 probe | TC-U-015, TC-U-051
SF-08 | Safe-stop on watchdog timeout | d | Function + timing + watchdog fault + bus-off | TC-S-006, TC-U-021, TC-I-031, TC-I-032
SF-09 | Cable management | — | Inspection | TC-Q-046
SF-10 | 24 V SELV insulation + isolation | — | Inspection + leakage | TC-Q-044, TC-U-056, TC-U-059
SF-11 | Per-rail overcurrent | c | Function + sweep | TC-U-006
SF-12 | Workbench fixturing procedure | — | Procedure + inspection | TC-U-062, TC-Q-001
SF-13 | Gripper hold on power loss | c | Function + power-cut | TC-U-007, TC-U-064
SF-14 | Stator over-temp shutdown | c | Function + threshold sweep + HW backup | TC-U-005, TC-U-027, TC-U-053, TC-U-054
SF-15 | Motion-imminent annunciator | b | Function + perception | TC-U-016
SF-16 | ESD-safe assembly | — | Procedure | —
SF-17 | EMC shielded harness | — | Inspection + immunity test | TC-S-043
SF-18 | Acoustic enclosure (classroom) | — | Procedure | —
SF-19 | Respiratory PPE | — | Procedure | —
SF-20 | Two-handed lift procedure | — | Procedure | —
SF-21 | Teach-mode rest-break | — | Procedure | —
SF-22 | Indoor-only restriction | — | Inspection / procedure | TC-Q-002
SF-23 | Trajectory jerk limit | d | Function + boundary | TC-U-028, TC-I-034
SF-24 | Manual rearm after E-Stop | d | Function + procedure | TC-S-005, TC-I-022
SF-25 | RT scheduler watchdog | d | Function + deadline injection | TC-U-020, TC-I-032
SF-26 | Authenticated tele-op | c | Function + protocol misuse | TC-U-024, TC-U-025, TC-S-009, TC-Q-026
SF-27 | Idle session lock | b | Function + timer | TC-U-010, TC-S-009
SF-28 | Encoder plausibility | c | Function + saturation injection | TC-U-023, TC-U-029, TC-S-020
SF-29 | Software joint limits | c | Function + boundary | TC-U-011, TC-U-052
SF-30 | Singularity-aware IK | c | Function + boundary | TC-U-013, TC-U-030, TC-I-011
SF-31 | Camera default-off | b | Function + power-on | TC-U-039, TC-U-063, TC-Q-004

## 07_ISO10218v
ISO 10218 + TS 15066 V&V Coverage Matrix
Clause | V&V activity | Linked SF | Linked TC
10218-1 §5.4 | Performance of safety-related control system | SF-08, SF-25 | TC-S-006, TC-S-041
10218-1 §5.5.3 | Protective stop function (Cat 0/1) | SF-08 | TC-I-020, TC-I-021, TC-S-004, TC-S-021
10218-1 §5.10 | Limits to motion (joint speed, torque) | SF-03 | TC-U-001, TC-U-002, TC-S-003
10218-1 §5.12 | Operating modes | SF-08 | TC-U-003, TC-I-010
TS 15066 §5 | Quasi-static + transient contact limits | SF-01, SF-02 | TC-S-002, TC-S-045, TC-S-046
TS 15066 A.2 | Body-region pressure / force thresholds | SF-01 | TC-S-002
10218-1 §5.5.5 | Restart after protective stop | SF-24 | TC-S-005, TC-I-022

## 03_UnitTests
Unit-level tests
TC-ID | Level | Title | Linked req(s) | SF / Hazard / FM | Pre-conditions | Test steps | Expected result | Pass criteria | Method | Owner
TC-U-001 | U | Joint torque limit clamp | SYRS-003, SRS-004 | SF-03 / HZ-M01 / FM-01 | Bench harness; commanded torque 1.5× joint limit | Inject cmd>limit; run cycle; read driver setpoint | Setpoint = configured torque limit | ≤ 100 % of declared ± 1 % | T-Unit | FW
TC-U-002 | U | Joint velocity limit clamp | SYRS-004 | SF-03 / HZ-M04 | Inject vel cmd > limit | Run controller; read setpoint | Velocity clamped | ≤ 100 % declared ± 1 % | T-Unit | FW
TC-U-003 | U | Mode FSM transitions | SYRS-009, SRS-003 | SF-08 | Mock heartbeat + auth | Drive each transition with valid + invalid guards | Only valid transitions accepted | 0 false-accept / 0 false-reject in 32-case matrix | T-Unit | FW
TC-U-005 | U | Stator over-temp action | SYRS-012, SRS-010 | SF-14 / HZ-T01 / FM-03 | Inject thermistor 100 °C | Run loop; capture cmd torque | Torque reduced to 50 %; T>105 °C → 0 | Latency ≤ 200 ms | T-Unit | FW
TC-U-006 | U | Per-rail overcurrent | SYRS-013 | SF-11 / HZ-E02 | Bench supply at 1.5× rated | Trip event | Fuse opens within spec | All branches passing | T-Unit | EE
TC-U-007 | U | Gripper hold on power loss | SYRS-014 | SF-13 / FM-06 | Gripper holding 500 g | Cut motor power | Grasp held passively | 100 % retention in 30 trials | T-Unit | Mech
TC-U-010 | U | Idle session lock 30 s | SYRS-016, SRS-007 | SF-27 | Authenticated session, no commands | Wait 30 s; attempt motion | Session locks | Lock latency ≤ 30 s ± 1 s | T-Unit | FW
TC-U-011 | U | Software joint limit + end-stop | SYRS-017 | SF-29 / HZ-C05 | Cmd 110 % of soft limit | Run controller; observe | Trajectory clamped at software limit; mech end-stop unreached | 0 mech end-stop contacts in 100 cycles | T-Unit | FW
TC-U-012 | U | CAN bus-off → safe-stop | SYRS-021, SRS-009 | SF-08 / HZ-C01 / FM-11 | Bench CAN harness with controllable transceiver | Force bus-off; observe response | Single recovery; on second occurrence → safe-stop | Safe-stop ≤ 100 ms | T-Unit | FW + EE
TC-U-013 | U | Pinocchio IK damped LSQ | SYRS-024, SRS-014 | SF-30 / HZ-C07 / FM-22 | Workspace boundary pose | IK; capture joint cmds | Joint speed bounded near singularity | No spike > 1.5× joint limit | T-Unit | FW
TC-U-014 | U | Wrist camera enumeration | SYRS-025 | FM-23 | Each supported camera mounted | Boot host; enumerate | All listed cameras detected | 5/5 cameras | T-Unit | FW
TC-U-015 | U | Pinch-zone gap probe ≤ 4 mm | SYRS-029, HWRS-006 | SF-07 / FM-27 | ISO 13854 finger probe | Probe each joint | Probe does not enter rotating zone | 0 entries | T-Unit | Mech
TC-U-016 | U | Motion-imminent annunciator | SYRS-035 | SF-15 | Robot in IDLE | Issue motion command | Annunciator fires ≥ 500 ms before motion | 30/30 trials | T-Unit | FW + UI
TC-U-020 | U | Loop deadline monitor | SRS-001 | SF-25 / FM-18 | Inject 5 consecutive 1.5× period misses | Trigger safe-stop | Safe-stop ≤ 100 ms | Latency window in 50 trials | T-Unit | FW
TC-U-021 | U | Heartbeat keep-alive | SRS-002 | SF-08 / HZ-C01 / FM-19 | Heartbeat at 4 Hz then stop | Stop heartbeat | Safe-stop ≤ 350 ms | Within 250+100 ms total | T-Unit | FW
TC-U-022 | U | Joint torque clamping at driver | SRS-004 | SF-03 / FM-01 | Cmd torque > limit | Run pipeline | Clamped output before drive | Within limit ± 1 % | T-Unit | FW
TC-U-023 | U | Encoder plausibility | SRS-005 | SF-28 / FM-04 | Inject torque-applied delta > bound for 25 ms | Run controller | Fault asserted within 20 ms | Detection ≤ 20 ms | T-Unit | FW
TC-U-024 | U | TLS 1.3 enforcement | SRS-006 | SF-26 / HZ-C02 / FM-20 | Test client offering TLS 1.2 only | Attempt connect | Connection refused | 0 % accept in 100 trials | T-Unit | FW
TC-U-025 | U | Token rotation | SRS-007 | SF-26 | Active session 8 h | Wait 8 h; attempt cmd | Token expired; cmd refused | Refusal ≥ 8 h ± 1 min | T-Unit | FW
TC-U-026 | U | Bus-off response | SRS-009 | SF-08 / FM-11 | Inject bus-off twice in 1 s | Observe FW | Recovery + safe-stop on 2nd | Safe-stop ≤ 100 ms | T-Unit | FW
TC-U-027 | U | Stator over-temp staircase | SRS-010 | SF-14 | Heat stator stepwise | Capture FW response 80/90/100/105/110 °C | Behaviour matches spec | Thresholds within ± 2 °C | T-Unit | FW + EE
TC-U-028 | U | Trajectory jerk limit | SRS-012 | SF-23 / HZ-P02 | Cmd unrealistic jerk profile | Run smoother | Jerk bounded by configured cap | Spectrum bound met | T-Unit | FW
TC-U-029 | U | Sensor freshness gate | SRS-013 | SF-28 / FM-04 | Inject 60 ms-old reading | Run controller | Reading rejected | 0 use of stale data in 1000 cycles | T-Unit | FW
TC-U-030 | U | Singularity-aware IK | SRS-014 | SF-30 / FM-22 | Drive workspace boundary trajectory | Run IK | Velocity bounded; no joint runaway | 100 % bounded | T-Unit | FW
TC-U-031 | U | Mode-change ack | SRS-015 | — | Send M command | Measure ack | Ack ≤ 50 ms | p95 ≤ 50 ms | T-Unit | FW
TC-U-032 | U | Idempotent commands | SRS-016 | — | Resend stale-timestamp cmd | Observe FW | Stale cmd ignored | 100 % rejection | T-Unit | FW
TC-U-033 | U | No torque on init | SRS-017 | HZ-C01 | Power-on with manipulator load | Observe joints | Zero torque until M(IDLE) authenticated | 0 motion at boot | T-Unit | FW
TC-U-034 | U | Telemetry framing | SRS-018 | — | Run telemetry stream | Capture 1 min | Sequence numbers monotonic ≥ 100 Hz | ≤ 0.1 % drop | T-Unit | FW
TC-U-035 | U | UI staleness gate | SRS-024 | FM-19 | Inject 250 ms staleness | Observe UI | Motion blocked, watermark visible | 100 % gating | T-Unit | UI
TC-U-036 | U | Config file signature | SRS-027 | — | Tampered config | Boot | Config rejected; safe defaults | 0 accept of unsigned | T-Unit | FW
TC-U-037 | U | LeRobot policy clamping | SRS-030 | SF-01,SF-03 / FM-21 | Mock policy outputs 2× joint limits | Run pipeline | Outputs clamped before drive | 0 violations in 1e6 cycles | T-Unit | FW
TC-U-038 | U | Time sync host↔motor | SRS-031 | — | PTP / chrony test | Sample 1000 timestamps | Skew ≤ 1 ms | p99 ≤ 1 ms | T-Unit | FW
TC-U-039 | U | Wrist-camera privacy controls | SRS-036 | SF-31 / FM-23 | Camera fitted | Default state on boot | Camera default-off; enable requires confirm | Pass 5/5 | T-Unit | FW + UI
TC-U-040 | U | Variant detection | SRS-037 | SF-29 / FM-26 | Mismatched motor profile | Boot | RUN refused; clear error | Refusal in 5/5 trials | T-Unit | FW
TC-U-050 | U | Sharp-edge inspection | HWRS-005 | SF-05 / HZ-M03 / FM-08 | ISO 13854 4 mm probe | Probe accessible exterior | No edge < 4 mm radius | Pass on every candidate edge | T-Unit | Mech
TC-U-051 | U | Pinch-zone gap | HWRS-006 | SF-07 / FM-27 | ISO 13854 finger probe | Probe each joint | Gap ≤ 4 mm or labyrinth blocks | 0 entries | T-Unit | Mech
TC-U-052 | U | Mech end-stop position | HWRS-007 | SF-29 | Disable software limits | Drive joint | Mech contact ≥ 5° beyond software limit | Within ± 0.5° | T-Unit | Mech
TC-U-053 | U | Stator thermistor calibration | HWRS-008 | SF-14 | Reference calibrator at 25/50/75/100 °C | Read thermistor | Reading ± 2 °C | All points within ± 2 °C | T-Unit | EE
TC-U-054 | U | Hardware thermal cutoff | HWRS-009 | SF-14 / FM-03 | Heat motor branch 1.5× rated | Observe rail | Cutoff opens within 5 s | All branches passing | T-Unit | EE
TC-U-055 | U | Connector pull test | HWRS-011 | FM-13 | Pull-test fixture | Apply 50 N to crimp | No detachment, no degradation | All connectors | T-Unit | Harness
TC-U-056 | U | Reverse polarity protection | HWRS-012 | SF-10 / FM-15 | Bench supply | Apply reversed voltage | No damage; no current flow | 0 damage in 5 trials | T-Unit | EE
TC-U-057 | U | E-Stop annunciator | HWRS-015 | SF-08 / FM-17 | 2 m viewing distance | Toggle armed/disarmed | State legible | Pass at 2 m / 30 lux | T-Unit | EE
TC-U-058 | U | UVLO + power-good | HWRS-016 | SF-13 / FM-14 | Programmable supply 22 V → 24 V | Sweep; capture PG | PG asserts at 22 V; glitch filtered | ± 50 mV | T-Unit | EE
TC-U-059 | U | Keyed PSU connector | HWRS-018 | SF-10 / FM-15 | Mating fixture | Verify reverse mate | Reverse mate impossible | 0 reverse mates | T-Unit | EE
TC-U-060 | U | ESD ±8 kV contact | HWRS-020 | HZ-E03 | ESD gun per IEC 61000-4-2 | Discharge to each connector | No damage; resumes ≤ 5 s | Pass on all | T-Unit | EE
TC-U-061 | U | Mass and reach static check | HWRS-024, SYRS-010 | HZ-G01,HZ-M06 | Calibrated scale + tape | Weigh / measure reach | Mass ≤ 5 kg; reach ≤ 700 mm | ± 0.5 kg / ± 20 mm | T-Unit | Mech
TC-U-062 | U | Base mounting interface | HWRS-025 | SF-12 / HZ-M06 | M6 fixture plate | Verify hole pattern + thread | 100 × 100 mm pattern, M6 ×4 | Pass | T-Unit | Mech
TC-U-063 | U | Camera privacy LED | HWRS-028 | SF-31 / FM-23 | Wrist camera fitted | Start / stop record | LED on while recording, off otherwise | 100 % deterministic | T-Unit | EE
TC-U-064 | U | Gripper mech hold | HWRS-029 | SF-13 / FM-06 | Gripper grasp 500 g | Cut power 30× | Grasp held | 30/30 | T-Unit | Mech
TC-Q-001 | U | Workbench fixturing checklist exists | SYRS-007 | SF-12 | Operator manual | Verify checklist mandatory before power-on | Present and prominent | Pass | I | Docs
TC-Q-002 | U | Indoor / dry restriction documented | SYRS-018 | — | Operator manual | Verify restriction clearly stated | Present | Pass | I | Docs
TC-Q-003 | U | 24 V PSU spec documented | SYRS-019 | SF-10 | Operator manual + BOM | Verify PSU spec ≥ 15 A continuous | Present | Pass | I | EE + Docs
TC-Q-004 | U | Camera default-off + privacy doc | SYRS-026 | SF-31 / FM-23 | Operator manual | Verify privacy section + recording opt-in | Present | Pass | I | Docs
TC-Q-005 | U | Git log review | SYRS-027 | — | Repo + commit log | Audit last 50 commits | All reference issue/PR | 100 % | I | QMS
TC-Q-006 | U | Mill-cert review | SYRS-028 | FM-07 | 5 mill certs | Cross-check material | All match BOM | 5/5 | I | QMS
TC-Q-007 | U | Reach safeguarding plan | SYRS-030 | HZ-M04 | Cell drawing | Verify ISO 13857 distances | Documented for each OE-2/3 cell | Pass | I | Integrator
TC-Q-008 | U | Sim-to-real parity check | SRS-035 | HZ-C06 | Isaac Sim model + real measurement | Compare kinematic params | ≤ 5 % deviation | All joints | T,A | Sim
TC-Q-009 | U | Variant compatibility doc | SYRS-033 | FM-26 | BOM + FW spec | Verify documented differences DM/RS | Present | Pass | I | Project
TC-Q-010 | U | Operator manual completeness | SYRS-034 | — | manual | Verify limits/warnings/E-Stop test/LOTO/maintenance | All present | Pass | I | Docs
TC-Q-020 | U | Audit log retention | SRS-008 | HZ-C02 | Operate session | Verify logs accessible 30 days later | Pass | Pass | I | FW
TC-Q-021 | U | Contract test suite in CI | SRS-020 | FM-19 | CI pipeline | Trigger build | Suite executed; failures block merge | Pass | I | Test eng
TC-Q-022 | U | Secure boot enforcement | SRS-021 | HZ-C02 | Tampered FW image | Attempt boot | Bootloader rejects | 0 boots of unsigned | T | FW
TC-Q-023 | U | Diagnostic log export | SRS-022 | — | Operate | Export 24 h log | Complete and parseable | Pass | I | Host
TC-Q-024 | U | MISRA-C / Rust safe analysis | SRS-025 | — | CI build | Run static analyser on safety-tagged code | 0 mandatory violations | 0 mandatory | T | Test eng
TC-Q-025 | U | Unit test coverage ≥ 80 % | SRS-026 | — | CI build | Run suite with coverage | ≥ 80 % statement coverage | ≥ 80 % | T | Test eng
TC-Q-026 | U | TLS pinning | SRS-028 | HZ-C02 | App with wrong cert | Attempt connect | Refused | 0 accept | T | UI
TC-Q-027 | U | FW rollback | SRS-032 | — | Inject corrupted FW | Trigger update | Rollback to last good | Pass | T | FW
TC-Q-028 | U | UDS-style diag | SRS-033 | — | Diag tool on motor bus | Read DTC | Returns valid response | Pass | T | FW
TC-Q-029 | U | Vulnerability disclosure channel | SRS-034 | HZ-C02 | Project page | Verify channel + 30-day SLA | Present | Pass | I | Project
TC-Q-030 | U | Sim model parity | SRS-035 | HZ-C06 | Isaac Sim USD vs measured | Compare params | ≤ 5 % deviation | All joints | T,A | Sim
TC-Q-031 | U | Logging severity levels | SRS-038 | — | Operate | Set each level; capture output | Levels filterable | 5/5 | T | Host
TC-Q-040 | U | Sheet-metal mill cert review | HWRS-001 | FM-07 | 5 mill certs | Verify against BOM | Match | 5/5 | I | QMS
TC-Q-041 | U | FEA report on brackets | HWRS-002 | FM-07 | FEA model + drawing | Verify ≤ 0.5 σy | Pass on all | Pass | I,A | Mech
TC-Q-042 | U | Torque + threadlocker spec | HWRS-004 | FM-10 | Assembly manual | Verify each fastener has torque + grade | 100 % | 100 % | I | Docs
TC-Q-043 | U | Bus termination measurement | HWRS-010 | FM-11 | DMM on bus | Measure with bus down | ≈ 60 Ω | 50–70 Ω | T | EE
TC-Q-044 | U | Lockable disconnector spec | HWRS-013 | HZ-E01 | Drawing | Verify lockability | Lock applies | Pass | I | EE
TC-Q-045 | U | PSU minimum spec doc | HWRS-017 | FM-14 | Kit BOM | Verify ≥ 15 A continuous spec | Present | Pass | I | EE
TC-Q-046 | U | Harness routing drawing | HWRS-019 | FM-12 | Harness drawing | Verify radius and strain relief | Pass | Pass | I | Harness
TC-Q-047 | U | UV chamber soak — covers | HWRS-026 | FM-08 | Cover coupons in UV chamber | Soak 500 h; measure | Δ flexural ≤ 10 % | ≤ 10 % | T | Mech + supplier
TC-Q-048 | U | Wrist camera mount fit | HWRS-027 | — | Each supported camera | Mount + secure | All bolt up | 5/5 | I | Mech
TC-Q-049 | U | Cable spec | HWRS-030 | FM-12 | Cable spec sheet | Verify gauge + shielding | Match BOM | Pass | I | EE
TC-Q-050 | U | WEEE marking | HWRS-031 | — | Electronics | Inspect for marking | Symbols present | Pass | I | EE

## 04_IntegTests
Integration tests
TC-ID | Level | Title | Linked req(s) | SF / Hazard / FM | Pre-conditions | Test steps | Expected result | Pass criteria | Method | Owner
TC-I-001 | I | Mode FSM end-to-end | SYRS-009 | SF-08 | Robot powered, host booted | Drive each transition from operator app | All transitions match guard table | All pass | T,D | FW + Test
TC-I-003 | I | Motor bus integration | SYRS-020 | SF-08 / FM-11 | Full harness assembled | Bring up bus; query 7 nodes; force bus-off | All nodes up; bus-off recovers per SRS-009 | Pass | T | FW + EE
TC-I-010 | I | Mode transition guard matrix | SRS-003 | SF-08, SF-26 | Auth + mocks | Drive 16-row truth table (E-Stop × Auth × HB × Limits) | Only all-OK rows enter RUN | All 16 behave as table | T | FW
TC-I-011 | I | Singularity behaviour | SRS-014 | SF-30 | Real arm + planner | Drive trajectory through workspace boundary | Velocity bounded; no joint runaway | Pass | T,D | FW + Test
TC-I-012 | I | API version mismatch reject | SRS-019 | FM-26 | Host with v1 message on v2 driver | Send command | Driver rejects with version-error | 0 % accept | T | FW
TC-I-013 | I | Cat 3 channel independence | SRS-001, SRS-005 | SF-08 | Static analysis + design docs | Audit watchdog + encoder-plausibility for shared cause | Independence demonstrated | Pass | A,I | Safety + FW
TC-I-020 | I | E-Stop press → motor power off | SYRS-005 | SF-08 / HZ-C01 / FM-16 | Robot in RUN | Press E-Stop | Motor power off ≤ 500 ms | Latency ≤ 500 ms in 30 trials | T | EE + Safety
TC-I-021 | I | E-Stop interlock at boot | SRS-023 | SF-08 / FM-25 | Robot off; E-Stop button removed | Power on | Motor enable refused; clear error | 0 enable in 5 trials | T | EE + FW
TC-I-022 | I | E-Stop manual rearm | SYRS-006 | SF-24 / FM-17 | Post-E-Stop press | Release; observe | Robot stays in ESTOP; manual rearm required | 0 silent restart | T | FW
TC-I-023 | I | Power-on self-test gate | SRS-011 | SF-08, SF-28 | Cold boot with simulated encoder fault | Attempt RUN entry | Self-test fails; RUN inhibited | 0 RUN entry | T | FW
TC-I-024 | I | Time sync 24 h | SRS-031 | — | Host + motors | Run 24 h | Skew ≤ 1 ms p95 | p95 ≤ 1 ms | T | FW
TC-I-025 | I | Operator presence (cobot mode) | SRS-029 | SF-06 | OE-2/3 mode | Suspend pings | Speed reduced or hold | Latency ≤ 5 s | T | FW + UI
TC-I-026 | I | Connector environmental thermal | HWRS-021 | FM-13 | Climate chamber | Cycle harness 100× | 0 broken connections | 0/100 | T | Harness
TC-I-030 | I | Camera + UI staleness guard | SRS-024 | FM-19 | Camera + host + tele-op UI | Inject 250 ms staleness | UI gate active; motion blocked | 100 % gating | T | UI
TC-I-031 | I | Bus simultaneous load | SYRS-020 | SF-08 | All 7 nodes populated | Run worst-case load 1 h | 0 bus-off; latency margin ≥ 30 % | Pass | T | FW + EE
TC-I-032 | I | Watchdog + HW WDT chain | SRS-001 | SF-25 | Block FW watchdog feed | Observe HW WDT reset | Reset within 10 ms; safe state held | Pass on 5 | T | FW + EE
TC-I-033 | I | Tele-op session resume | SYRS-022 | HZ-C01 / FM-19 | Operator app | Disconnect 30 s; reconnect | Watchdog → safe-stop; explicit re-arm + M(RUN) | No silent re-take | T | FW + Host
TC-I-034 | I | Trajectory smoothing integration | SRS-012 | SF-23 / HZ-P02 | Real arm | Drive aggressive cmd profile | Output jerk-limited | All within bound | T | FW
TC-I-035 | I | Variant DM ↔ RS interchange | SYRS-033 | FM-26 | Both motor variants on test bench | Boot with each | Auto-detect; refuse mismatch | Pass | T | FW
TC-I-040 | I | ROS2 driver + MoveIt2 | SYRS-031 | — | ROS2 driver + MoveIt2 | Plan and execute pick | Plan executes within limits | Pass | T,I | FW
TC-I-041 | I | LeRobot policy harness | SYRS-023 | SF-01,SF-03 / FM-21 | Real arm + LeRobot stack | Run benchmark policy | Outputs clamped; safe completion | Pass / no faults | T | FW
TC-I-042 | I | Pinocchio FK/IK accuracy | SYRS-024 | SF-30 | Calibrated TCP marker | Compare Pinocchio FK to ground truth | Error ≤ 1 mm at 0.5 m extension | Pass | T,A | FW + Test
TC-I-043 | I | Wrist camera + perception | SYRS-025 | FM-23 | Real arm + camera | Run YOLO grasping demo | Detect + grasp succeed; recording LED matches | Pass | T,D | Test

## 05_SystemTests
System / validation tests
TC-ID | Level | Title | Linked req(s) | SF / Hazard / FM | Pre-conditions | Test steps | Expected result | Pass criteria | Method | Owner
TC-S-001 | S | Pose accuracy + repeatability | SYRS-010, SYRS-011 | — | OE-1 lab; clamped to bench | Run ISO 9283 cube test | Repeatability < 0.2 mm; pose accuracy declared | All joints meet spec | T | Mech + Test
TC-S-002 | S | ISO/TS 15066 PFL measurement | SYRS-002 | SF-01,SF-02 / GAP-15066-01 | Force/pressure pad fixture | Run all body-region tests per TS 15066 Table A.2 | All measurements ≤ thresholds | All categories pass | T | Test + Safety
TC-S-003 | S | Joint torque overload protection | SYRS-003 | SF-03 / HZ-M01 | Bench fixture loading single joint | Apply 1.5× nominal external torque | FW reduces commanded torque; no actuator damage | 0 damage in 10 trials | T | Test
TC-S-004 | S | E-Stop response | SYRS-005 | SF-08 / FM-16 | Robot in RUN | Press E-Stop | Motor power off ≤ 500 ms | 30/30 within 500 ms | T | Test
TC-S-005 | S | Manual rearm | SYRS-006 | SF-24 | Post-E-Stop | Release; attempt M(IDLE) | Robot stays in ESTOP until manual rearm | 0 silent restart in 30 trials | T | Test
TC-S-006 | S | Watchdog soak | SYRS-008 | SF-08 | Robot in RUN | Cycle disconnect every 60 s for 1 h | Each disconnect → safe-stop ≤ 350 ms | 60/60 cycles ≤ 350 ms | T | Test
TC-S-007 | S | Reach + payload | SYRS-010 | — | OE-1 bench | Drive arm to 70 % reach with 1.5 kg payload | Pose held; no fault | Pass at 5 poses | T | Test
TC-S-008 | S | Repeatability (extended) | SYRS-011 | — | Lab repeatability fixture | Run 1000 cycles to fixed target | Std dev < 0.2 mm | Within spec | T | Test
TC-S-009 | S | Auth + idle-lock end-to-end | SYRS-015 | SF-26, SF-27 | Operator app | Authenticated session; leave idle 60 s | Lock at 30 s | Pass | T | Host + Test
TC-S-010 | S | Tele-op latency budget | SYRS-022 | — | OE-1 LAN | Run 1 h tele-op | p95 latency ≤ 50 ms | p95 ≤ 50 ms | T | Host + Test
TC-S-011 | S | LeRobot policy verification | SYRS-023 | SF-01,SF-03 / GAP-LP-01 | Real arm + policy library | Run policy across hazard catalogue | All scenarios safe or escalate to safe-stop | 100 % safe outcome | T,A | Robotics + Test
TC-S-012 | S | ROS2 driver smoke test | SYRS-031 | — | Native ROS2 install | Bring up driver + sample motion | All nodes start; motion executes | Pass | T,I | FW
TC-S-020 | S | Boot self-test gate | SRS-011 | SF-08, SF-28 | Cold boot with injected fault | Observe RUN attempt | Self-test fails; RUN inhibited | 0 RUN entry | T | FW + Test
TC-S-021 | S | E-Stop interlock end-to-end | SRS-023 | SF-08 / FM-25 | Robot fully off | Power on without E-Stop installed | Motor enable refused; clear UI message | Pass | T | Test
TC-S-022 | S | Operator presence (cobot) | SRS-029 | SF-06 | OE-2/3 cobot mode | Run 1 h with intermittent ping suspension | Each → reduced-speed or hold | 100 % within 5 s | T | Test
TC-S-040 | S | Subassembly load cycle | HWRS-003 | FM-07 | Per-bracket fixture | 1×10⁶ cycles at 1.5× nominal | No fatigue | All pass | T | Mech + Test
TC-S-041 | S | E-Stop architecture validation | HWRS-014 | SF-08 / GAP-10218-02 | ISO 13849-2 procedure | Function, single fault, accumulation | All test procedures pass | All pass | T,A | Safety + Test
TC-S-042 | S | Operating temp soak | HWRS-021 | HZ-V02 | Climate chamber | Soak +10 / +35 °C, run typical workload 1 h each | No thermal shutdown | Pass at both | T | Test
TC-S-043 | S | EMC immunity | HWRS-022 | HZ-E04 | EMC chamber | Run immunity sweep | No safety-impacting upset | Pass per EN 61000-6-2 | T | EMC lab
TC-S-044 | S | EMC emissions | HWRS-023 | — | EMC chamber | Run emissions sweep | Below limits | Pass per EN 61000-6-3 | T | EMC lab
TC-S-045 | S | Quasi-static contact head | SYRS-002 | SF-01 / HZ-P01 | Force pad on head reference | Drive trajectory toward pad | Force ≤ TS 15066 head-region threshold | Pass | T | Test
TC-S-046 | S | Transient hand impact | SYRS-002 | SF-02 / HZ-P02 | Pad on hand reference | Drive impact at varying speed | Force ≤ 280 N | Pass | T | Test

## 08_TraceMatrix
Test → Requirement Trace Matrix
TC-ID | Level | Title | Reqs | SF / HZ / FM | Method
TC-U-001 | U | Joint torque limit clamp | SYRS-003, SRS-004 | SF-03 / HZ-M01 / FM-01 | T-Unit
TC-U-002 | U | Joint velocity limit clamp | SYRS-004 | SF-03 / HZ-M04 | T-Unit
TC-U-003 | U | Mode FSM transitions | SYRS-009, SRS-003 | SF-08 | T-Unit
TC-U-005 | U | Stator over-temp action | SYRS-012, SRS-010 | SF-14 / HZ-T01 / FM-03 | T-Unit
TC-U-006 | U | Per-rail overcurrent | SYRS-013 | SF-11 / HZ-E02 | T-Unit
TC-U-007 | U | Gripper hold on power loss | SYRS-014 | SF-13 / FM-06 | T-Unit
TC-U-010 | U | Idle session lock 30 s | SYRS-016, SRS-007 | SF-27 | T-Unit
TC-U-011 | U | Software joint limit + end-stop | SYRS-017 | SF-29 / HZ-C05 | T-Unit
TC-U-012 | U | CAN bus-off → safe-stop | SYRS-021, SRS-009 | SF-08 / HZ-C01 / FM-11 | T-Unit
TC-U-013 | U | Pinocchio IK damped LSQ | SYRS-024, SRS-014 | SF-30 / HZ-C07 / FM-22 | T-Unit
TC-U-014 | U | Wrist camera enumeration | SYRS-025 | FM-23 | T-Unit
TC-U-015 | U | Pinch-zone gap probe ≤ 4 mm | SYRS-029, HWRS-006 | SF-07 / FM-27 | T-Unit
TC-U-016 | U | Motion-imminent annunciator | SYRS-035 | SF-15 | T-Unit
TC-U-020 | U | Loop deadline monitor | SRS-001 | SF-25 / FM-18 | T-Unit
TC-U-021 | U | Heartbeat keep-alive | SRS-002 | SF-08 / HZ-C01 / FM-19 | T-Unit
TC-U-022 | U | Joint torque clamping at driver | SRS-004 | SF-03 / FM-01 | T-Unit
TC-U-023 | U | Encoder plausibility | SRS-005 | SF-28 / FM-04 | T-Unit
TC-U-024 | U | TLS 1.3 enforcement | SRS-006 | SF-26 / HZ-C02 / FM-20 | T-Unit
TC-U-025 | U | Token rotation | SRS-007 | SF-26 | T-Unit
TC-U-026 | U | Bus-off response | SRS-009 | SF-08 / FM-11 | T-Unit
TC-U-027 | U | Stator over-temp staircase | SRS-010 | SF-14 | T-Unit
TC-U-028 | U | Trajectory jerk limit | SRS-012 | SF-23 / HZ-P02 | T-Unit
TC-U-029 | U | Sensor freshness gate | SRS-013 | SF-28 / FM-04 | T-Unit
TC-U-030 | U | Singularity-aware IK | SRS-014 | SF-30 / FM-22 | T-Unit
TC-U-031 | U | Mode-change ack | SRS-015 | — | T-Unit
TC-U-032 | U | Idempotent commands | SRS-016 | — | T-Unit
TC-U-033 | U | No torque on init | SRS-017 | HZ-C01 | T-Unit
TC-U-034 | U | Telemetry framing | SRS-018 | — | T-Unit
TC-U-035 | U | UI staleness gate | SRS-024 | FM-19 | T-Unit
TC-U-036 | U | Config file signature | SRS-027 | — | T-Unit
TC-U-037 | U | LeRobot policy clamping | SRS-030 | SF-01,SF-03 / FM-21 | T-Unit
TC-U-038 | U | Time sync host↔motor | SRS-031 | — | T-Unit
TC-U-039 | U | Wrist-camera privacy controls | SRS-036 | SF-31 / FM-23 | T-Unit
TC-U-040 | U | Variant detection | SRS-037 | SF-29 / FM-26 | T-Unit
TC-U-050 | U | Sharp-edge inspection | HWRS-005 | SF-05 / HZ-M03 / FM-08 | T-Unit
TC-U-051 | U | Pinch-zone gap | HWRS-006 | SF-07 / FM-27 | T-Unit
TC-U-052 | U | Mech end-stop position | HWRS-007 | SF-29 | T-Unit
TC-U-053 | U | Stator thermistor calibration | HWRS-008 | SF-14 | T-Unit
TC-U-054 | U | Hardware thermal cutoff | HWRS-009 | SF-14 / FM-03 | T-Unit
TC-U-055 | U | Connector pull test | HWRS-011 | FM-13 | T-Unit
TC-U-056 | U | Reverse polarity protection | HWRS-012 | SF-10 / FM-15 | T-Unit
TC-U-057 | U | E-Stop annunciator | HWRS-015 | SF-08 / FM-17 | T-Unit
TC-U-058 | U | UVLO + power-good | HWRS-016 | SF-13 / FM-14 | T-Unit
TC-U-059 | U | Keyed PSU connector | HWRS-018 | SF-10 / FM-15 | T-Unit
TC-U-060 | U | ESD ±8 kV contact | HWRS-020 | HZ-E03 | T-Unit
TC-U-061 | U | Mass and reach static check | HWRS-024, SYRS-010 | HZ-G01,HZ-M06 | T-Unit
TC-U-062 | U | Base mounting interface | HWRS-025 | SF-12 / HZ-M06 | T-Unit
TC-U-063 | U | Camera privacy LED | HWRS-028 | SF-31 / FM-23 | T-Unit
TC-U-064 | U | Gripper mech hold | HWRS-029 | SF-13 / FM-06 | T-Unit
TC-Q-001 | U | Workbench fixturing checklist exists | SYRS-007 | SF-12 | I
TC-Q-002 | U | Indoor / dry restriction documented | SYRS-018 | — | I
TC-Q-003 | U | 24 V PSU spec documented | SYRS-019 | SF-10 | I
TC-Q-004 | U | Camera default-off + privacy doc | SYRS-026 | SF-31 / FM-23 | I
TC-Q-005 | U | Git log review | SYRS-027 | — | I
TC-Q-006 | U | Mill-cert review | SYRS-028 | FM-07 | I
TC-Q-007 | U | Reach safeguarding plan | SYRS-030 | HZ-M04 | I
TC-Q-008 | U | Sim-to-real parity check | SRS-035 | HZ-C06 | T,A
TC-Q-009 | U | Variant compatibility doc | SYRS-033 | FM-26 | I
TC-Q-010 | U | Operator manual completeness | SYRS-034 | — | I
TC-Q-020 | U | Audit log retention | SRS-008 | HZ-C02 | I
TC-Q-021 | U | Contract test suite in CI | SRS-020 | FM-19 | I
TC-Q-022 | U | Secure boot enforcement | SRS-021 | HZ-C02 | T
TC-Q-023 | U | Diagnostic log export | SRS-022 | — | I
TC-Q-024 | U | MISRA-C / Rust safe analysis | SRS-025 | — | T
TC-Q-025 | U | Unit test coverage ≥ 80 % | SRS-026 | — | T
TC-Q-026 | U | TLS pinning | SRS-028 | HZ-C02 | T
TC-Q-027 | U | FW rollback | SRS-032 | — | T
TC-Q-028 | U | UDS-style diag | SRS-033 | — | T
TC-Q-029 | U | Vulnerability disclosure channel | SRS-034 | HZ-C02 | I
TC-Q-030 | U | Sim model parity | SRS-035 | HZ-C06 | T,A
TC-Q-031 | U | Logging severity levels | SRS-038 | — | T
TC-Q-040 | U | Sheet-metal mill cert review | HWRS-001 | FM-07 | I
TC-Q-041 | U | FEA report on brackets | HWRS-002 | FM-07 | I,A
TC-Q-042 | U | Torque + threadlocker spec | HWRS-004 | FM-10 | I
TC-Q-043 | U | Bus termination measurement | HWRS-010 | FM-11 | T
TC-Q-044 | U | Lockable disconnector spec | HWRS-013 | HZ-E01 | I
TC-Q-045 | U | PSU minimum spec doc | HWRS-017 | FM-14 | I
TC-Q-046 | U | Harness routing drawing | HWRS-019 | FM-12 | I
TC-Q-047 | U | UV chamber soak — covers | HWRS-026 | FM-08 | T
TC-Q-048 | U | Wrist camera mount fit | HWRS-027 | — | I
TC-Q-049 | U | Cable spec | HWRS-030 | FM-12 | I
TC-Q-050 | U | WEEE marking | HWRS-031 | — | I
TC-I-001 | I | Mode FSM end-to-end | SYRS-009 | SF-08 | T,D
TC-I-003 | I | Motor bus integration | SYRS-020 | SF-08 / FM-11 | T
TC-I-010 | I | Mode transition guard matrix | SRS-003 | SF-08, SF-26 | T
TC-I-011 | I | Singularity behaviour | SRS-014 | SF-30 | T,D
TC-I-012 | I | API version mismatch reject | SRS-019 | FM-26 | T
TC-I-013 | I | Cat 3 channel independence | SRS-001, SRS-005 | SF-08 | A,I
TC-I-020 | I | E-Stop press → motor power off | SYRS-005 | SF-08 / HZ-C01 / FM-16 | T
TC-I-021 | I | E-Stop interlock at boot | SRS-023 | SF-08 / FM-25 | T
TC-I-022 | I | E-Stop manual rearm | SYRS-006 | SF-24 / FM-17 | T
TC-I-023 | I | Power-on self-test gate | SRS-011 | SF-08, SF-28 | T
TC-I-024 | I | Time sync 24 h | SRS-031 | — | T
TC-I-025 | I | Operator presence (cobot mode) | SRS-029 | SF-06 | T
TC-I-026 | I | Connector environmental thermal | HWRS-021 | FM-13 | T
TC-I-030 | I | Camera + UI staleness guard | SRS-024 | FM-19 | T
TC-I-031 | I | Bus simultaneous load | SYRS-020 | SF-08 | T
TC-I-032 | I | Watchdog + HW WDT chain | SRS-001 | SF-25 | T
TC-I-033 | I | Tele-op session resume | SYRS-022 | HZ-C01 / FM-19 | T
TC-I-034 | I | Trajectory smoothing integration | SRS-012 | SF-23 / HZ-P02 | T
TC-I-035 | I | Variant DM ↔ RS interchange | SYRS-033 | FM-26 | T
TC-I-040 | I | ROS2 driver + MoveIt2 | SYRS-031 | — | T,I
TC-I-041 | I | LeRobot policy harness | SYRS-023 | SF-01,SF-03 / FM-21 | T
TC-I-042 | I | Pinocchio FK/IK accuracy | SYRS-024 | SF-30 | T,A
TC-I-043 | I | Wrist camera + perception | SYRS-025 | FM-23 | T,D
TC-S-001 | S | Pose accuracy + repeatability | SYRS-010, SYRS-011 | — | T
TC-S-002 | S | ISO/TS 15066 PFL measurement | SYRS-002 | SF-01,SF-02 / GAP-15066-01 | T
TC-S-003 | S | Joint torque overload protection | SYRS-003 | SF-03 / HZ-M01 | T
TC-S-004 | S | E-Stop response | SYRS-005 | SF-08 / FM-16 | T
TC-S-005 | S | Manual rearm | SYRS-006 | SF-24 | T
TC-S-006 | S | Watchdog soak | SYRS-008 | SF-08 | T
TC-S-007 | S | Reach + payload | SYRS-010 | — | T
TC-S-008 | S | Repeatability (extended) | SYRS-011 | — | T
TC-S-009 | S | Auth + idle-lock end-to-end | SYRS-015 | SF-26, SF-27 | T
TC-S-010 | S | Tele-op latency budget | SYRS-022 | — | T
TC-S-011 | S | LeRobot policy verification | SYRS-023 | SF-01,SF-03 / GAP-LP-01 | T,A
TC-S-012 | S | ROS2 driver smoke test | SYRS-031 | — | T,I
TC-S-020 | S | Boot self-test gate | SRS-011 | SF-08, SF-28 | T
TC-S-021 | S | E-Stop interlock end-to-end | SRS-023 | SF-08 / FM-25 | T
TC-S-022 | S | Operator presence (cobot) | SRS-029 | SF-06 | T
TC-S-040 | S | Subassembly load cycle | HWRS-003 | FM-07 | T
TC-S-041 | S | E-Stop architecture validation | HWRS-014 | SF-08 / GAP-10218-02 | T,A
TC-S-042 | S | Operating temp soak | HWRS-021 | HZ-V02 | T
TC-S-043 | S | EMC immunity | HWRS-022 | HZ-E04 | T
TC-S-044 | S | EMC emissions | HWRS-023 | — | T
TC-S-045 | S | Quasi-static contact head | SYRS-002 | SF-01 / HZ-P01 | T
TC-S-046 | S | Transient hand impact | SYRS-002 | SF-02 / HZ-P02 | T

## 10_References
References
Reference | Title
IEEE 829-2008 | Software and System Test Documentation
ISO 13849-2:2012 | Validation of safety-related parts of control systems
ISO 10218-1/-2:2011 | Industrial robot safety
ISO/TS 15066:2016 | Collaborative robot PFL data
ISO 12100:2010 | Safety of machinery
ISO 9283 | Robot performance
EN 61000-6-2 / -6-3 | EMC immunity / emissions
REBOT-SC-CP-001 | Safety Case
REBOT-DFMEA-CP-001 | DFMEA
REBOT-REQ-CP-001 | Requirements
REBOT-ARCH-CP-001 | Architecture